| NO | DATE | ENQUIRY | RESPONSE FROM TEAM |
| --- | --- | --- | --- |
|  | 4 December 2024 | Good afternoon. We are an architectural practice engaged to provide theming and theming related designs for The Developer, working together with the submitting architect, to provide a themed waterpark. As such, for our last two payment, the client has delayed payment of which our latest invoice was sent on the 5th February 2024 which till now is pending. We would like to give notice to suspend our services but there is no provisions in our LOA for such course of action. In our notice, can we refer to the Architects Rules 1996 for the suspension of services? Also, are there panel lawyers that PAM can refer us to that are familiar with contract and construction laws related to construction? Thank you for your kind attention to the matter. | Thank you for your enquiry dated 4 December 2024. We would write in reply as follows: - Based on your very brief description of the services provided by yourself, we are unable to ascertain if the services provided fall under the ambit of architectural consultancy services as defined under the Architects (Scale of Minimum Fees) Rules (SoMF) and as such, whether your appointment would be subject to the SoMF as well as the Conditions of Engagement as prescribed under the Architects Rules 1996 (Third Schedule). We would advise that you refer again to the services under your Letter of Appointment relative to those under the SoMF for further guidance. Should the services offered by yourselves fall under the definition of architectural consultancy services under the SoMF, please be reminded that it is mandatory that these services are provided wholly in accordance with the SoMF (Rule 29, Architects Rules 1996) and would note that the suspension of services is allowed for under the above Conditions of Engagement. Apart from outlining the procedure for the suspension of services, these Conditions also have provisions for the resolution of any disputes which may arise (including those related to the payment of fees). In addition to the provisions under the Conditions of Engagement, you may also want to consider other legal avenues (i.e.; such as those provided under the Construction Industry Payment and Adjudication Act (CIPAA)) to resolve any disputes you may have regarding your fees. - PAM unfortunately, does not have any panels of lawyers or consultants to which members may refer to. We would advise that you check with your peers, colleagues and/or legal advisors for any recommendations. |
|  | 21 November 2024 | I am writing to seek guidance regarding defects encountered in a commercial office strata development administered under the PAM Contract 2006. Two specific incidents have raised questions about obligations and liabilities, and I would appreciate clarification on the following matters: - First Incident - Consequential Damage Due to Non-Compliance with Drawings During the Defects Liability Period (DLP), the roof gutter failed during heavy rain, causing flooding to the unit owner A's renovated interior space. Upon investigation, it has been confirmed that the roof gutter was not constructed in accordance with the drawings issued by the Architect. Following an instruction issued by the Architect under Clause 15.5 to make good defects, the contractor rectified the defect. However, the furniture and interior items in the unit were damaged as a result of the leakage. The amount received from the JMB's insurance company does not cover the amount claimed by the unit owner, as a significant portion of the claim relates to consequential losses from the water damage. Question: Who is obligated to bear the costs of all consequential damages resulting from such defects? Is the contractor responsible for damages that extend beyond the direct costs of rectifying the defective work? - Second Incident - Further Leakage Detected (Post-DLP) Following the expiration of the DLP and before the issuance of the Certificate of Making Good Defects (CMGD), a second leakage in the same unit A was detected in the roof gutter. Upon inspection, it has been determined that this defect also arises from the incorrect construction of the roof gutter and constitutes a latent defect as defined under Clause 15.5 of the PAM Contract 2006. To resolve the issue urgently and permanently, we intend to engage a third-party contractor to rectify the defect in accordance with Clause 30.4 of the PAM Contract 2006. Under this clause, the Employer is entitled to employ others to carry out the rectification works if the contractor fails to do so, and to recover the costs incurred from the contractor by way of set-off from payments due to the contractor. Question: As the DLP has expired, can we proceed to engage a third-party specialist to rectify this latent defect and recover the associated costs from the original contractor? | We refer to your email dated 25th November 2024, based on the information provided, please refer to our feedback as follows: Consequential Losses and PAM Contract 2006 The PAM Contract 2006 does not address claims for consequential losses from defects. Such claims are usually pursued between the purchaser and developer through tort. The developer may also consult their legal advisor to pursue any claims against the Contractor. Roof Gutter Failure and Defects You mentioned that leaks after the Defect Liability Period (DLP) were due to incorrect installation, calling it a latent defect. Correct gutter installation should have been inspected at Practical Completion and identified as a patent defect if non-compliant. It is prudent to support your claim of a latent defect. Note that "latent defect" is not defined under Clause 15.5 of the PAM Contract 2006. Contractor’s Obligation for Defects Clause 15.4 of the PAM Contract 2006 requires the contractor to rectify defects listed in the Schedule of Defects (SOD) after the DLP. If defects are not noted in the SOD, the Contractor may not need to rectify them. Detailed review of Clause 15 is recommended for more information on processes and limitations. Note that clauses 15.3, 15.4, and 15.5 allow hiring others to correct defects within the DLP and recovering costs under clause 30.4. However, employing others to rectify defects noted after the DLP and recovering those costs is beyond the provisions of the PAM Contract 2006. We recommend that you consult with your senior colleagues or the principal in charge regarding the matter, as they possess the necessary knowledge and have a better understanding of the context related to your query. |
|  | 15 November 2024 | Merujuk kepada perkara di atas, pihak kami senaraikan permasalahan berikut: - Jenis Kontrak: Condition of Contract for Design and Build Contract PWD Form DB (Rev.1/2010). - Situasi: - Pihak Pemaju: - Bercadang mendapatkan Certicate of Completion and Compliance (CCC) sebelum Certificate of Practical Completion (CPC). - Adakah ia dibolehkan dan pihak kami memerlukan rujukan (klausa) bagi perkara ini. - Bercadang untuk membawa Non-Compliances Report (NCR) dicatit sebagai “Defect” dan melaksanakan pembaikan pada Defect Liability Period (DLP) disebabkan tekanan terhadap pembeli dan pelbagai pihak tertinggi. - Kami memerlukan nasihat dan pandangan terhadap cadangan ini. - Pihak Konsultan: - Tiada bayaran fi (tambahan) kepada pihak konsultan bagi kos dan kerja-kerja semasa tamatnya tempoh kontrak atau Extension of Time (EOT) selama 4 tahun (Oktober 2021 – September 2024). - Pihak kami memerlukan rujukan dan klausa berkaitan bagi mengukuhkan tuntutan kami. - Bercadang menahan pengeluaran CCC sehingga pihak pemaju dan kontraktor menyelesaikan tuntutan pembayaran. - Adakah terdapat cara lain selain menahan CCC bagi menuntut bayaran tersebut. | We refer to your queries as received by email on the 15th November 2024. Based on the limited information provided, kindly note the following:- - Completion of the Works Clause There are notable differences in the certification process for completion across various types of building contracts, such as design-and-build and lump sum contracts. It is advisable to review the specific conditions of each contract to understand their requirements. - Non-Compliance Reports By "Non-Compliance Reports" (NCR), we understand this to mean reports identifying works that the contractor has not yet complied with or completed prior to achieving Practical Completion. Since the Defects Liability Period (DLP) commences only after Practical Completion, it is unclear how NCRs would be applicable or function during the DLP as mentioned in your query. - Architect’s Fees An architect's fees are governed by the terms of their appointment. As we are not aware of the specifics of your appointment, we recommend referring to your agreement for guidance on Additional Professional Fees for services rendered post-contract or during any delays. - Payment of Professional Fees The payment of professional fees, aligned with the stages of work completed, is typically governed by the architect's appointment terms. For any concerns about the suspension or withholding of services, we advise reviewing the relevant clauses in your appointment document. All architects are required to be fully aware of their conditions of appointment and the responsibilities that come with it. As very little information has been provided to us, we are loath to volunteer any assumptions to help you understand your responsibilities and would strongly advise that you study your own appointment/ Consultancy Agreement carefully to assist yourself in arriving at a resolution. |
|  | 5 November 2024 | We cannot agree on the amount of fees for work done. We are looking at arbitration as the way out. Please advise how to kickstart the process. And appreciate your information on duration to settle the process. | We refer to your query received on 5th November 2024 regarding the initiation of the arbitration process between an Architect and his Employer, and we would like to write to note the following: As a fellow professional, you may be aware that managing fee-related matters, including arbitration if needed, generally falls within contractual and professional responsibilities. These procedures are typically outlined in the initial agreement or, where relevant, within the LAM Conditions of Engagement. For added clarity, we recommend consulting with legal counsel to confirm the best approach. While PAM does not maintain records or specific details on arbitration timelines between architects and clients, we understand that the duration can vary depending on factors such as the complexity of the dispute and the commitment and expertise of the parties involved, including the arbitrator. The PAM Practice Bureau is here to assist with general inquiries related to professional practice. However, it remains important to consider the unique aspects of your appointment and to apply your professional judgment in navigating this process. |
|  | 9 July 2024 | Request for Advice on Dispute Between AI and Variation Order. | We refer to your enquiry received on 9th July 2024 regarding the dispute between the Architect’s Instruction (AI) and the Variation Order (VO). Based on the limited information provided, we shall reply with reference to the PAM Contract 2018 (With Quantities) as follows: - Validation of Clause 11.2 In accordance with Clause 2.1 of the PAM Contract 2018, the Contractor is obligated to fully comply with any Architect's Instruction (AI) issued. This compliance extends to the provisions of a Variation Order (VO) under Clause 11.2, stating that “Pending the valuation of the Variations, the Contractor shall carry out with due diligence and expedition all Variations so instructed.” The clauses expressly state that the Contractor shall proceed with the Variation prior to the completion of the valuation. - Protection Against Quotation Adjustments We recommend that the Contractor adhere strictly to the Conditions of Contract. To substantiate a Variation, the Contractor must submit detailed and comprehensive records and documentation of costs incurred to the Quantity Surveyor (QS) and the Architect upon completion of the Variation works. Valuation for such Variation will be carried out by the QS in accordance with the Valuation Rules under Clause 11.6, which stipulates valuation methods based on various scenarios. Recognizing the potential for additional expenses caused by Variation works, the PAM Contract 2018 mandates that the Contractor notify the Architect within the timeframe and procedures specified in Clause 11.7 for any Variation works requiring additional expenses not covered under the Valuation Rules in Clause 11.6. - Best Practices It is crucial for the Contractor to strictly adhere to the Conditions of Contract as a whole. Relevant clauses in the Contract specify the required documentation, submission procedures, and the timeline for dealing with Variations. Therefore, the Contractor should maintain detailed records and complete documentation, and act accordingly for the valuation of Variations. |
|  | 14 June 2024 | Developer has different opinion in the stump definition in Schedule of Payment of 2(a) in S&P agreement as per attached Sketch 1. I hope PAM can give better clarification in order for accurate certification. | We refer to your enquiry as received by e-mail on the 14th June 2024. Kindly note the following: - From your attachment, it would seem that your enquiry is based on the Lembaga Arkitek Malaysia's General Circular No. 2/2017 which provides guidelines for the certification of stage completion for housing under Sale and Purchase Agreements (SPAs) provided for under the Housing Development (Control and Licensing) Regulations 1989. Based on the above, we would normally advise that you consult the Architect in charge as; - all Architects should have the required knowledge and an understanding of the context to ascertain completion of any of the relevant stages; and - regardless of any differences of opinion between the Architect and his Employer or fellow consultants, they are the party responsible for stage certification under the afore-mentioned SPAs. - We note though that we have encountered definitions which describe the column stump as the connecting structural component from the top of a pile cap or footing to the top of the ground beam. Nevertheless, it is our opinion that any definition should be taken within the context of the above General Circular and the stages contained under the Third Schedule of the above SPAs. - For the stages in the Third Schedule, there is a clear differentiation between; - "The foundation of the said Building" (Stage 2(a)) and - "The structural framework of the said Building" (Stage 2(b)) The above-mentioned General Circular further elaborates by noting that; - for Stage 2(a), this includes "All foundation works below the lowest floor level" inclusive of any stumps; - for Stage 2(b), this includes "All primary structural elements above lowest floor level (sic.)" including beams. In reading the above, it is our opinion that; - any structural element below the lowest floor level; i.e., pile caps, footings or stumps, would be considered as part of the foundations and be under stage 2(a); - any structural element starting from the lowest floor level such as the ground beams would in turn, be considered as part of the structural framework under stage 2(b); - following on from the above and with regards to the portion coloured red in "Case 1" of your attached Sketch 1, it is our considered opinion that the structural engineer should provide advice and justification based on the scope of work described, considering the nature of the structural elements in relation to their function and the overall structural system. - The above should also be considered with respect to best practices when undertaking construction; would the portion coloured red in "Case 1" be cast together with the pile cap or would it be constructed together with the surrounding ground beams? - Although the PAM Practice Bureau is willing to stand by its opinions, PAM is unfortunately not in a position to provide any official clarification on this issue as we are neither the authors of the afore-mentioned SPAs or General Circular nor are we the bodies tasked with enforcing these documents. Should you require a more conclusive answer, we would suggest you contact the Ministry of Housing and Local Government and the Lembaga Arkitek Malaysia with your enquiry. - Finally, we would also note that although the above General Circular provides "Guidelines" which all Architects are expected to follow, these Guidelines do not provide the same level of finality which may be found under primary legislation (such as the Housing Development (Control and Licensing) Act or secondary legislation (such as the Housing Development (Control and Licensing) Regulations. We trust the above has been of assistance. |
|  | 13 March 2024 | Last year we have terminated the main contractor due to their non performance. During termination partly of the works has been constructed by the main contractor i.e; some of foundations works and partly structure works. We had appointed a new main contractor to resume and complete the works. The issue who should sign the G forms? The new main contractor reluctant to sign the G1-G4 forms with reason the are not the one who construct the works from the early. Whilst the previous main contractor also deny to sign since they are not completing the works. Can the G1-G4 forms signed by 2 different main contractor? | Thank you for your inquiry dated 13th Mar 2024. Your query pertains to 1) the party responsible for the signing of the G1-G4 forms and 2) if the above forms may be signed by two distinct contractors for the project. Taking your first query, kindly note that the G Forms are for certification upon completion of specific works/tasks; it would follow as such, that they are required to be signed by the parties completing the relevant works/tasks. As for the second query, as far as we are aware, there are no provisions for the division of responsibility for a specific task under the above G forms to more than one party unless such division of the work has been clearly indicated on the approved Building Plan. Considering the termination of the previous main contractor and the involvement of a new contractor, we would suggest consulting with the local authority on the requirements of G forms for works involving old and new contractors. With regards to the Contractors' reluctance to sign any of the forms, we would advise that you refer to your Notice of Determination (Old Contractor), Letters of Award, Conditions of Contract and Contract Documents to check if any provisions have been made with respect to the contractors' certification under the relevant forms. You may also want to check with your Architect or Contract Administrator for clarification as they should be familiar with all of the above documents. For works which have commenced under one main contractor but are required to be completed by another, it is normal practice for the second contractor to be selected not just on his competence and pricing but also on his agreement to accept responsibility for all the relevant works. You may want to review the award to your second contractor to confirm this. We would advise the Employer to discuss with the new Contractor on the terms and conditions which may be acceptable for him to accept the responsibilities attached to the relevant G forms. We hope this information is helpful to you. |